## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
TDHS representative to attend Region meetings to explore advocacy work within the region | In progress | This strategy was started in February 2022. The strategy to attend regional meetings and engage in advocacy work faced challenges due to resource constraints, staff turnover, budget restrictions, and organisational restructures. These factors hindered consistent implementation and disrupted continuity in regional engagement efforts. The Health Service Partnership program proposed a utility to support the implementation of the Gender Equality Act at 0.5 FTE per month however this did not eventuate. Addressing these challenges will be a priority and will require strategic planning and resource allocation to ensure effective and sustained regional engagement initiatives.
Display posters and visual reminders throughout the health service regarding gender equality | Not started | This strategy has not yet been implemented. The Diversity and Inclusion Committee was created and discontinued in 2022 due to a lack of clear structure and purpose, making its effectiveness uncertain. Without defined objectives or roles and resources to support implementation of work generated by the committee, the committee struggled to demonstrate its impact on advancing diversity and inclusion efforts within the organisation. Consequently, Executive leadership made the decision to discontinue the committee. The discontinuation of the Diversity and Inclusion Committee has prompted the organisation to re-evaluate its approach to fostering diversity and inclusion. In response, a new committee is currently being created to address this imperative. This committee will be accountable for ensuring that diversity and inclusion initiatives are effectively implemented and aligned with organisational goals. By establishing clear objectives and fostering collaboration among stakeholders, the new committee aims to drive meaningful change and create a more inclusive workplace culture.
Board to review Purpose Statement and clarify that their practice aligns every 2 years | Ongoing | This strategy was implemented in June 2022. The Board approved the Gender Equality Purpose Statement in June 2022 with a commitment to biennial reviews. We have implemented a revised schedule within the sub-board committee of People, Culture and Remuneration's annual work plan to ensure regular ongoing reviews.
Creation and implementation of Diversity and Inclusion calendar events | Complete | This strategy was implemented in September 2023, and post the reporting period. The creation and implementation of the Diversity and Inclusion calendar events have been completed to foster a more inclusive and equitable workplace environment. To ensure the successful creation and management of the events calendar, a dedicated working group was formed to oversee the process. This working group consists of individuals from various departments and levels within the organisation, reflecting the diversity of perspectives and experiences that the events calendar aims to celebrate. To ensure alignment with organisational goals and priorities, the calendar is reviewed by the executive team on a monthly basis. This regular review process provides an opportunity for the executive team to provide guidance, offer insights, and make strategic decisions regarding the events calendar.
Significant dates such as international women's day, 16 days of activism etc. celebrated and recognised on TDHS Facebook page and through internal events | Ongoing | This strategy was implemented on XX. Our community engagement strategy encompasses the media plan, outlining the acknowledgment of significant dates. We have adopted and implemented this strategy throughout the organisation and across our online platforms. Additionally, this approach has been mirrored in the Diversity and Inclusion calendar of events.
Family Violence information added to TDHS intranet page including contact officer information | In progress | This strategy was implemented on 14 February 2024. While a Family Violence procedure was reviewed 13 September 2023, outlining contact officer information, additional steps were necessary to publish these details on our intranet site for convenient access by all staff members. This implementation occurred recently, with the delay attributed to inadequate planning of this task.
TDHS participate at region SHRFV and MARAM information sessions | Ongoing | Attendance has been observed at SHRFV and MARAM information sessions; however, active participation has been challenging due to resource and time constraints. From 14 February 2024, we have engaged a Family Violence Officer to help support the creation and implementation of both programs of work.
Family Violence procedures and practices reviewed and updated if necessary | Complete | This strategy was implemented on 21 October 2021. The Family Violence Procedure underwent a review and update on 13 September 2023. The review process confirmed that no changes were deemed necessary at that time, indicating that the procedure remains current and aligned with organisational requirements. This review cycle ensures that the procedure is regularly assessed to maintain its effectiveness and relevance in addressing family violence issues within the organisation.
Data gaps from Workplace Audit outlined | In progress | We are in the process of implementing a new Human Resources Information System which will capture new data sets. We are still evaluating our manual processes to ensure data gaps are located.
Current procedures relating to sexual harassment are reviewed and amended if necessary to reflect best practice | Complete | This strategy was implemented on 10 September 2021. The Sexual Harassment Procedure underwent a review on 15 May 2023. During the review process, it was determined that no amendments were required to the procedure. This reaffirms the effectiveness and relevance of the procedure in addressing and preventing sexual harassment within the organisation. The regular review cycle ensures that the procedure remains up-to-date and aligned with evolving organisational needs and best practices.
Positive responses through the People Matter Survey results | Void/cancelled | As an organisation, we have come to realise that positive responses through the People Matter Survey results may not serve as an effective strategy or measure for assessing our performance. Therefore, we have decided to void or cancel this action. Moving forward, we plan to review the indicator it aligns with to reassess our best options.
Review employees on part-time arrangements to determine which qualify as flexible work arrangements | In progress | This strategy started in September 2023. The review of part-time employees for flexible work arrangements has begun but remains incomplete due to staffing issues, turnover, budget constraints, ongoing system implementations, and the need for leader education. Limited resources and time have hindered progress in achieving this outcome. Despite challenges, efforts are underway to address these obstacles and expedite the completion of the review process. In addition, we will be implementing the Flexible Work Arrangement Committee to act as an advisory board to the organisation when assessing flexible work arrangements.
Gender pay gaps are investigated and reported to CEO for review and rectifiction | Not started | The investigation and reporting of gender pay gaps to the CEO for review and rectification have not commenced due to several reasons. Firstly, staff fall under enterprise agreements, which necessitate careful consideration and alignment with existing contractual frameworks. Additionally, the organisation's information systems lack the necessary capabilities to facilitate such investigations effectively. Furthermore, a formal review process has not yet been established, primarily because HR lacks the time, resources, and funding required to initiate and complete this action. These constraints have impeded progress in addressing gender pay gaps within the organisation. Despite these challenges, efforts are underway to identify and implement viable solutions to enable the investigation and rectification of gender pay disparities in the future. In addition, and post implementation of the GEAP, our organisational structure has been changed to include a HR Manager position who we recognise will now be responsible to review and rectify gender pay gaps.
Increase in positive responses to Diversity and Inclusion questions in People Matter Survey | Void/cancelled | The initiative to increase positive responses to Diversity and Inclusion questions in the People Matter Survey requires review as it lacks clarity. Further analysis is essential to determine the most suitable assessment approach for this item, including gathering feedback and assigning responsibilities to the revamped diversity and inclusion committee.
Gender Impact Assessments are conducted on new and existing policies, programs and services with direct and significant impact on the public | Not started | Due to turnover within the executive team and organisational restructuring over the previous 14 months, the organisation has not conducted training for any leaders, nor have any assessments been carried out.
Gender Equality Action Plan is published on the TDHS Intranet | Complete | This strategy was implemented on 14 February 2024. The GEAP was uploaded onto the intranet, allowing all staff members to access and review it. The goal is to provide additional education to staff regarding the purpose and objectives of the Gender Equality Act and as it applies to their roles.
Executive leadership team leads the role out of Gender Impact Assessments | Not started | Executive team turnover and organisation restructure has meant that the orgnsiation has not conducted training for any leaders and no assessments have been made.
All members of the executive leadership team undertakes Diversity and Inclusion training | Not started | Executive team turnover and organisation restructure has meant that the orgnsiation has not conducted training for any leaders and no assessments have been made.
MARAM plan created and implemented | Not started | Planned for action in the second year.
Family Violence education and information sessions rolled out to supervisor and managers | Not started | Not yet commenced as planned for action in year 2.
Develop strategies to capture missing workforce data for new and existing staff with a specific focus on capturing intersectional data in line with Privacy Act Legislation | Not started | Not yet commenced as planned for action in year 2.
Intersectional data gaps identified and a strategy is put in place to capture this information from new and existing employees | Not started | Not yet commenced as planned for action in year 2.
Review current complaints record keeping system for workplace sexual harrassment and align to best practice | Not started | Not yet commenced as planned for action in year 2.
Trial blind recruitment process with supervisor/manager recrutiment | Not started | Not yet commenced as planned for action in year 2.
Flexible work arrangement details recorded in Chris21 with review dates | Not started | Not yet commenced as planned for action in year 2.
Training and development programs for leadership positions are implemented | Not started | Not yet commenced as planned for action in year 2.
Committee meetings have online options (zoom) for attendance | Not started | Not yet commenced as planned for action in year 2.
Clear procedures outlining how to complete Gender Impact Assessments are included on PROMPT | Not started | Not yet commenced as planned for action in year 2.
Strategy to formally capture higher duties, flexible work arrangements and promotions of existing employees is implemented | Not started | Not yet commenced as planned for action in year 3.
All data is recorded in Chris21 system with the exception of Sexual Harassment complaints and Family Violence records | Not started | Not yet commenced as planned for action in year 3.
Workplace sexual Harrassment Strategy - Add KPI's to timeframes in which complaints must be delat with | Not started | Not yet commenced as planned for action in year 3.
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
Over the course of our efforts to complete the Gender Equality Act reporting, we have encountered a multitude of challenges stemming from various factors within our organisational framework. Paramount among these obstacles has been the persistent lack of adequate resources, which has hindered our ability to effectively allocate personnel, time, and funding toward the completion of the Gender Equality Act report. This deficiency in resourcing has not only impeded progress but has also limited our capacity to address critical aspects of the submission in a timely manner such as the Gender Impact Assessments of which none were completed for the reporting period. Both our former CEO and HR Coordinator were aware of and were institutional in creating and submitting the Gender Equality Action Plan and associated data. Turnover in this domain led to a re-evaluation of responsibilities, but advancement was limited until last year's organisational restructuring where the role of HR Manager was instituted into our organisational structure. Currently, one full-time HR Manager handles the Gender Equality Act implementation amidst their substantial workload. An additional 0.1 FTE has recently supported submission efforts. Despite obstacles, our HR team is committed to meeting GEAP requirements and promoting gender equality within our organisation. Compounding our resource constraints, we have also grappled with financial deficits that have constrained our ability to invest in essential tools, technologies, and expertise necessary for comprehensive assessment and planning. This financial shortfall has forced us to prioritise certain activities over others, often at the expense of critical components of the Gender Equality Act report. Moreover, our organisation has been overwhelmed by competing priorities that have diverted attention and resources away from the Gender Equality Act report. In the face of pressing operational demands and strategic initiatives, it has been challenging to maintain a singular focus on the completion of the submission. Another significant hurdle has been the absence of robust systems and reporting mechanisms tailored to support the implementation of the Gender Equality Act report. Without adequate infrastructure in place, tracking progress, identifying bottlenecks, and coordinating efforts across teams have proven to be arduous tasks, further impeding our ability to meet key milestones. Additionally, turnover at the executive level has introduced instability and disruption to our organisational leadership. With changes in key leadership positions occurring in three out of the four roles pertinent to the reporting, there has been a notable loss of institutional knowledge and continuity, further complicating our efforts to move the plan forward. Furthermore, an organistional restructure initiated to optimise workflow and clarify executive responsibilities has only recently been completed, with the devolution and realignment of work to appropriate executive stakeholders finalised in late 2023. This restructuring process, though ultimately beneficial in streamlining operations, has necessitated significant adjustments and acclimatisation among staff members, further contributing to delays in Gender Equality Act reporting. We are submitting this report fully cognisant of the ongoing challenges we face in completing the requirements to meet the Gender Equality Act. We recognise the complexities involved and the hurdles that have impeded our progress thus far. As we move forward, any support that can be provided would be greatly appreciated. Addressing the resource constraints, aligning priorities, strengthening reporting mechanisms, and ensuring stability in leadership are crucial steps in our journey towards successful implementation. Your continued support and collaboration are invaluable as we strive to uphold our commitment to Gender Equality in the workplace.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | The analysis of employee experience data from 2021 to 2023 reveals a noteworthy enhancement in diversity across the organisation's workforce. However, it is important to note that these improvements are characterised by modest increases in various areas. This improvement can be attributed to the implementation of various strategies, including the Diversity and Inclusion Calendar, associated working groups, and the integration of significant dates through Facebook. Despite these initiatives, there remains ample room for further progress in this domain. Enhancements such as data collection refinement, the review of payroll/data systems for enhanced reporting capabilities, oversight of the Gender Equality Action Plan (GEAP), and reporting activities to the Board via the People, Culture, and Remuneration sub-committee of the Board have been identified as areas for development. Moreover, the establishment of a Diversity and Inclusion Committee aims to ensure accountability in plan implementation. Acknowledging our responsibilities under the Gender Equality Act, it is imperative to recognise that the implementation of such measures will necessitate additional workload for staff, potentially impacting time management and stress levels. Compounded by the financial constraints stemming from post-COVID-19 deficits, the organisation has faced challenges in allocating resources towards a dedicated position for Gender Equality Act implementation. In terms of workforce composition, there were three fewer participants in 2023 compared to 2021. Staff identifying as women experienced a 1% increase, while men decreased by 3%. Additionally, there was a 1% increase in individuals identifying as Other and those preferring not to disclose their gender. Regarding individuals identifying as trans, non-binary, or gender diverse, one person identified as such in 2023, whereas 2021 saw no identification. Meanwhile, 56 individuals did not identify, and 17 preferred not to disclose in 2023, indicating a change from 71 and 10, respectively, in 2021. The composition of the executive team also saw shifts, with the 2021 team comprising entirely of women. In contrast, the 2023 executive team included a male CEO, with women constituting 67% and men 33% of the team. Furthermore, sexual orientation exhibited increased diversity, with four out of five categories experiencing an uptick. Notably, one category saw no indication listed year-on-year. Changes in percentages include a 6% decrease in individuals identifying as hetrosexual, a 6% increase in those preferring not to disclose, and 1% increases in both bisexual and asexual identifications. Meanwhile, a 3% decrease was observed in those indicating "don't know," and a 1% increase in the use of alternative terms. Finally, regarding disability identification, there was a 5% increase in individuals identifying as having a disability, a 4% decrease in those indicating no disability, and a 1% decrease in those preferring not to disclose. In conclusion, while strides have been made in fostering diversity and inclusion within the organisation, ongoing efforts are required to address challenges and ensure continued progress in gender equality and workforce diversity.
Gender composition of governing bodies | No | The gender composition of our governing body has experienced a decline, with the number of men decreasing from 3 to 1 between the 2021 and 2023 reporting periods. Conversely, there has been no change in the representation of women, remaining at 6 members throughout both periods. Notably, none of the board members self-described their gender identity. These figures parallel those observed within the workforce, where 10% identified as men, 90% identified as women, and none identified as self-described. As mentioned above, there are opportunities to reassess our data collection methods concerning all aspects of intersectionality within our Board. This endeavour will facilitate a deeper understanding of diversity within the Board and its impact on the organisation as a whole. The promotion of gender equality within the board, as outlined in our Gender Equality Action Plan (GEAP), is encapsulated within a single Board Purpose Statement. However, the construction process of this statement remains unclear, particularly considering that many other health services lack such a statement. The board holds itself accountable to decisions aligning with this statement and undergoes a biennial review process. Presently, we are engaging with our People, Culture, and Remuneration sub-committee of the Board to delve deeper into the purpose of this statement and establish metrics that facilitate the board's understanding of decision-making congruent with its purpose. This evaluation underscores the necessity of considering our 2025 GEAP, focusing on how we engage with the Board and ensuring that progress metrics are both measurable and serve a common goal aligned with the Gender Equality Act.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | No | In the reporting system, only data for women is available. Based on the available information, the median base salary indicates a negative pay gap of 10.1% in 2023 compared to -5.9% in 2021. Several factors contribute to this disparity: - The aging workforce has led to more staff opting for casual employment over permanent positions. - Employees returning from parental leave often choose to reduce their hours permanently or revert to casual employment for increased flexibility. - In 2022, the organisation initiated a traineeship program, resulting in incumbents being listed under traineeship wages instead of those specified in the enterprise agreement. As outlined in the Gender Equality Action Plan (GEAP), any gender pay gaps are to be investigated and reported to the CEO for review and rectification. With a recent organisational restructuring and the appointment of an HR Manager, the responsibility for addressing pay gaps now falls under the purview of the HR Manager, overseen by the CEO. To further support this initiative, we intend to explore additional opportunities, including: - Conducting classification reviews of position descriptions. - Reviewing traineeships and associated classifications to ensure fairness. - Promoting transition to retirement and other employment terms and conditions such as flexible work arrangements and family violence leave. - Establishing a mentoring program to encourage staff contemplating retirement to engage, thereby enhancing our ability to provide support and facilitate a smooth transition into retirement for our employees.
Sexual harassment in the workplace | No | Despite the absence of available data within our reporting system, insights from our employee experience results indicate a consistent prevalence of sexual harassment in the workplace, with approximately 3% of staff reporting such experiences over the preceding three years. This translates to fewer than 10 reported cases annually. While these numbers are relatively low, the consistency of reported incidents raises concerns, particularly as staff have not actively sought assistance through our organisational processes. This lack of engagement with internal procedures may stem from various factors, including unawareness of available processes, mistrust in the efficacy of the reporting system, or apprehensions regarding potential retaliation. Our GEAP identifies several actions and progress measures under the workplace sexual harassment strategy. Items include: • Ensure policy and procedure reflect best practice • Demonstrate inappropriate behaviours will be dealt with by reducing the timeframe for resolution of discipline matters • Review current complaints record keeping system and align to best practice • Positive responses through people matter survey results. While these actions support the sexual harassment indicator, they may not fully address the progress needed to create a harassment-free environment. Recognising this, we plan to incorporate additional actions to complement the GEAP's initiatives for this indicator. Moreover, implementing initiatives such as managerial training and establishing a peer support network for individuals experiencing sexual harassment and other negative behaviours can foster a sense of support and acknowledgment among staff. Such measures underscore the organisation's stance against unacceptable behaviour and its commitment to supporting affected individuals. A peer-to-peer program can empower staff to assess whether the behaviour they are experiencing warrants formal reporting, thereby safeguarding not only their own well-being but also that of their colleagues. Establishing trust in the reporting process is crucial for cultivating a work environment free from harassment and conducive to employee well-being and productivity.
Recruitment and promotion practices in the workplace | No | Our organisation faces limitations in accessing comprehensive data to understand various indicators fully. Despite this constraint, comparing data from 2023 to 2021 reveals significant insights: • Participation in the employee experience survey decreased by three employees in 2023. • L&D needs met increased by 6% in 2023. • Career progression declined by 8% in 2023. • Employees experienced barriers, with 15% citing physical health and 13% citing mental health issues in 2023. • Witnessed barriers to success, particularly mental health-related, increased to 17% in 2023. • Fairness in recruitment and promotion practices improved by 3% in 2023. • Equal chances at promotion decreased by 6% in 2023. • A gender composition analysis of our workforce post-recruitment in 2023 compared to 2021 indicates an 8% decrease for men and an 8% increase for women. Additionally, there was a 3% increase in exited staff identifying as men and a 3% decrease for women in 2023. Despite efforts, accurate data regarding staff self-identification remains limited, with self-described identification remaining constant at 0%. Unfortunately, several critical categories lack available data, including permanent positions, career development opportunities, higher duties, and internal secondments. This gap underscores deficiencies in our organisational processes and systems for accurate data collection, a focus area within our existing Gender Equality Action Plan (GEAP). While our GEAP prioritises fair and transparent recruitment and promotion practices, we recognise the need for enhanced intersectionality awareness and support. To address this, we propose several actions: • Develop a leadership training program with a specific focus on recruitment responsibilities. • Implement a multi-focal recruitment strategy targeting candidates of all ages, including school-age students, apprenticeships, and mature-age individuals. • Introduce an Aboriginal Liaison Officer to brand our organisation as a safe place for Indigenous employees. • Promote flexible work arrangements to support staff outside of work responsibilities. • Emphasize career progression and succession planning for all roles. • Manage our aging workforce by promoting transition to retirement programs and fostering mentorship relationships with junior staff. These actions aim to enhance our recruitment processes, promote inclusivity, and support career development across our organisation.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | In the workforce data section of our reporting system, it's evident that certain data is unavailable for the reporting period. For instance, information regarding senior leaders' flexible work arrangements, parental leave exits, and family violence leave is not accessible. However, carers leave emerges as a commonly utilised leave type, with 40 women and 3 men availing of it in 2023. Moreover, upon further intersectionality analysis, it's noted that a significant portion of carers leave is taken for school-age, preschool, and aged persons. Interestingly, under aged persons carers leave, it's observed that 100% of self-described staff take this type of leave, although it isn't reported under the workforce data tab. Additionally, about 33% of both men and women in our organisation do not utilise carers leave. Our employee experience survey results provide additional insights into three leave types: - The consideration for flexible work arrangements has declined by 5% in 2023. - Support for family violence leave has decreased by 10% in 2023. - Support for flexible work was not surveyed in 2021; however, our staff rated it at 72% in 2023. Our Gender Equality Action Plan (GEAP) targets specific areas across three strategies: flexibility and leave, family violence, and leadership. Key actions include: - Reviewing part-time staff to identify eligibility for flexible work arrangements. - Overhauling the system to record and track arrangements. - Conducting monthly staff meetings to address care and outside work responsibilities. - Providing education and information sessions to support managers in these discussions. - Reviewing and updating policies and procedures. - Having the executive team model genuine flexibility. Furthermore, we're exploring additional opportunities in the following areas: - Reviewing all staff contracts to ensure fairness in flexible working arrangements. - Establishing a flexible work committee to offer advice and guidance to staff and managers seeking flexible work arrangements and to aid in policy and procedure review. - Involving the Diversity and Inclusion Committee in policy and procedure review to ensure fairness and best practice. - Utilising the Diversity and Inclusion calendar and working group to promote activities across all intersectionality groups. - Promoting and educating all staff about available terms and conditions.
Gendered segregation within the workplace | Yes | The reporting system currently lacks available data; however, insights from our People Matter survey shed light on key aspects: - A decrease of 3 staff members participating in the survey was noted in 2023. - In 2023, 79% of staff feel comfortable being themselves at work. - There's a 16% decline in staff feeling culturally safe in 2023. - 67% of staff feel a sense of belonging within our organization in 2023. Embedded within our Gender Equality Action Plan (GEAP) are three fundamental principles: education, best practices in policy and procedures, and health service partnerships aimed at fostering organisational growth. Additionally, we have implemented or plan to implement the following actions: - Completed the restructure of the HR department, appointing a HR Manager to lead GE activities and be part of the executive team for continuous communication of people-related initiatives. - Establishing several committees to support HR activities and GEAP implementation, including the Workforce Committee, Diversity and Inclusion Committee, Flexible Work Committee, and Health and Safety Committee. - Initiated the People, Culture, and Remuneration sub-committee of the board for ongoing reporting of people matters to the Board. - Instituted weekly executive leadership meetings to facilitate continuous information sharing. - An upcoming budget review will propose an increase in HR FTE to execute organisational strategy and people-related activities, including GEAP. - The imminent implementation of the organisational strategy, which emphasises creating a great place to work. - The forthcoming implementation of the Human Resources Information System (HRIS) part one to bolster effective, efficient, and fair recruitment activities, with plans to adopt the remaining HRIS package in subsequent years. - A review of GEAP actions for years 2 and 3 to make necessary amendments and commence consultation for the 2025 GEAP.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled